## Backlog Simple Epics
Epic | User Story Title | Story | Value (Clinician) | Acceptance Criteria | Complexity | Time | Sprint
Sprint Initiation | Team setup & communication enablement | As a project team, we want roles allocated and shared comms/dev spaces so that collaboration is smooth and accountable. | Faster progress → earlier access to a usable diagnostic tool in clinic. | Roles defined; comms created; repo structured | S | 1 day | Sprint 0
Sprint Initiation | Group contract | As a team, we want a working agreement so that expectations and conflict resolution are clear. | Stable teamwork → reliable clinical model timeline. | Contract covers attendance, deadlines, rules etc | S | 1 day | Sprint 0
Sprint Initiation | Governance pack (charter + OKRs) | As a team, we want a charter and OKRs so that scope and outcomes are aligned. | Ensures clinical-focused model goals (accuracy, generalisation). | Charter includes stakeholders, constraints; OKRs tied to metrics | S | 2 Days | Sprint 0
Sprint Initiation | Risk assessment | As a team, we want a risk assesment so that blockers are prevented. | Stable development reduces risk of unsafe clinical output and prevents potentail risks from happening during model building which can save time and speed up the delivery of the product. | Risk assessment | M | 1 Day | Sprint 0
Research & Planning | Dataset audit & data dictionary | As a research and data team, we want to perform a full audit of the 3-Stim Auditory Oddball and Resting-State EEG dataset, covering dataset structure, participant grouping (PD vs Control), metadata, event markers, recording parameters, clinical labels, and data quality issues, and then produce a complete data dictionary to remove ambiguity before preprocessing and model development. | • Sampling rate verified across all files • Channel labels checked (montage, missing/bad channels) • Event markers validated (standard, target, deviant) • Resting-state noise scanning (eye blinks, HF noise, drift) • Metadata completeness assessed (age, PD/control labels, clinical scales) • Participant group table created (PD vs control, age ranges) • Data quality summary (line noise, dropped channels, missing data) | Sampling, channels, markers verified; dictionary made; DoD: markdown report committed.+ | L | 4 weeks | Sprint 1
Research & Planning | Methods review & pipeline decision | As a research team, we want a complete review of EEG processing and modelling techniques used for Parkinson’s diagnosis, including artifact types, removal methods, filtering best practices, feature extraction families, preprocessing, and modelling frameworks (EEGNet, CNN-LSTM, 1D/2D CNNs, Transformers), so that we can justify and select a default pipeline for the project. | Builds a clinically credible diagnostic workflow → higher trust, transparency, and likelihood of achieving useful sensitivity/specificity for Parkinson’s detection. | Artifact-Removal Review Feature Extraction Review Modelling Review Preprocessing Depth Pipeline Decision | L | 2 weeks | Sprint 1
Preprocessing | Preprocessing pipeline v1 (re-ref, filter, artifact detect/remove) | We want to develop a full end-to-end preprocessing pipeline for our dataset, including band-pass and notch filtering, automated artifact detection, and artifact removal so that the EEG data is clean, standardised, and ready for feature extraction and modelling. | Cleaner, high-quality EEG signals → reduced diagnostic errors, more reliable biomarkers, and better model performance. | Filtering implemented Artifact detection completed Artifact removal performed | XL | 2 weeks | Sprint 2
Preprocessing | Task segmentation & baseline correction | We want to segment the EEG into resting-state windows and properly aligned Oddball task epochs, including baseline correction, event marker validation, and rejection of invalid epochs, so that the dataset is temporally structured for reliable event-related analysis and modelling. | Improves clinician interpretation of evoked responses. | Resting-state segmentation Oddball epoch extraction Baseline correction performed | L | 2 weeks | Sprint 2
Modelling | Modelling Framework | We want to create a reliable and reproducible dataset split (train/val/test) and train a baseline EEGNet model, so that we establish an initial performance benchmark for Parkinson’s detection using both Resting-State and Oddball EEG. | Provides clinicians with the first diagnostic performance estimate (accuracy, F1, AUC), helping them understand the model’s initial sensitivity to Parkinsonian neural patterns. | Dataset Split Metrics Generated: Accuracy, Precision, Recall, F1-score, ROC curve + AUC, Confusion matrix, Loss + accuracy curves | M | 2 weeks | Sprint 3
Modelling | Regularisation & training protocols | We want to design and apply consistent regularisation strategies and training protocols, including dropout, batch normalisation, weight decay, and learning rate scheduling, so that our models generalise well across participants and avoid overfitting—especially important in clinical EEG where inter-subject variability is high. | Prevents overfitted models that might appear accurate in training but fail on real patients → reduces risk of clinically unsafe or misleading predictions. | Regularisation Techniques Implemented Training Stability Techniques Evaluation of Overfitting | XL | 2 weeks | Sprint 3
Evaluation | Evaluation & visualisations | We want a standardised evaluation suite that produces clear metrics and visualisations, including ROC, confusion matrices, calibration plots, and summary scores, so that model performance is transparent and comparable across experiments. | Helps clinicians interpret reliability. | ROC, PR, confusion matrix, calibration curve generated Summary metrics exported (AUC, F1, sensitivity, specificity, ECE) Visualisation templates finalised | M | 5 Days | Sprint 4