## Sheet1
| Tasks | Resource | Start Date | End Date | Duration(Days) | Dependencies | Importance | Notes | Oct | Nov | Dec | Jan | Feb | Mar
| Scrum 0 - Project Initiation | All
0.1 | Roles | J | 28/10/25 | 31/10/25 | 4 | - | Low
0.2 | Group Contract | All | 30/10/25 | 2025-02-11 | 4 | 0.1 | Low
0.3 | Communication Tools | J | 2025-01-11 | 2025-03-11 | 3 | 0.1 | Medium
0.4 | Project Charter | D | 2025-03-11 | 2025-06-11 | 4 | 0.2 | High | Define Project Scope & Deliverables
0.5 | OKRs | A | 2025-05-11 | 2025-08-11 | 4 | 0.4 | Medium | Set measurable goals & KPIs
0.6 | Risk Management Table | A | 2025-06-11 | 2025-10-11 | 5 | 0.4, 0.5 | High | Identify and rank project risks
| Scrum 1 — Research & Planning | All
1.1 | Understand Dataset Structure | All | 15/11/25 | 2025-05-12 | 21
1.1.1 | Inspect 3-Stim Auditory Oddball and Resting-State EEG dataset structure and metadata | All | 15/11/25 | 20/11/25 | 6 | 1.1 | High
1.1.2 | Identify participant groups (PD vs control), recording parameters (sampling rate, channels), and stimulus markers | All | 21/11/25 | 2025-01-12 | 10 | 1.1.1 | High | Verify sampling rate and stimulus markers
1.1.3 | Document data quality issues (missing channels, line noise) and available behavioral/clinical labels | All | 25/11/25 | 2025-05-12 | 11 | 1.1.2 | Medium
1.2 | Literature Mapping | All | 15/11/25 | 30/11/25 | 16
1.2.1 | Review state-of-the-art papers on Parkinson’s diagnosis using EEG and deep learning | All | 15/11/25 | 22/11/25 | 8 | 1.1 | Medium
1.2.2 | Study artifact types and their detection/removal performance metrics (F1, AUC, SNR gain) | J | 17/11/25 | 25/11/25 | 9 | 1.2.1 | High
1.2.3 | Compare main artifact-removal methods: ICA (Infomax/AMICA), ASR, MWF, CCA, EEMD, and hybrid stacks | J | 18/11/25 | 27/11/25 | 10 | 1.1, 1.2.2 | High | Evaluate strengths & weaknesses per artifact type
1.2.4 | Research adaptive, notch, and band-pass filtering best practices for EEG (0.5–45 Hz + 50 Hz notch) | A | 20/11/25 | 28/11/25 | 9 | 1.1 | Medium
1.2.5 | Investigate feature-extraction techniques: PSD, theta/alpha ratio, entropy, Hjorth, coherence, phase-locking, and time–frequency maps | D | 22/11/25 | 30/11/25 | 9 | 1.1 | High
1.2.6 | Study recent work on preprocessing impact (“how much cleaning helps”) to decide minimal vs hybrid pipelines | A | 25/11/25 | 2025-02-12 | 8 | 1.1, 1.2.1 | Medium
1.2.7 | Review modeling frameworks used in PD EEG research — EEGNet, CNN-LSTM, and Transformer-based models | A | 26/11/25 | 2025-03-12 | 8 | 1.1, 1.2.1 | High
1.3 | Summarize all findings in a methods-comparison table (advantages, limitations, and selected default pipeline) | All | 28/11/25 | 2025-04-12 | 7 | 1.1, 1.2 | High
1.4 | Environment & Library Setup | All | 25/11/25 | 2025-06-12 | 11 | 1.1, 1.2, 1.3 | Low | Test MNE, PyTorch, and scikit-learn imports
Scrum 2 — EEG Preprocessing
2.1 | Data Import & Inspection | All | 2025-09-12 | 2025-10-12 | 2 | 1.4 | High
2.2 | Re-referencing | D | 2025-11-12 | 2025-12-12 | 2 | 2.1 | Medium
2.3 | Artifact Detection | J | 15/12/25 | 19/12/25 | 5
2.3.1 | Automated detection via ICLabel (CNN-based ICA component labeling) and EEGdenoiseNet (supervised AE) | J | 15/12/25 | 17/12/25 | 3 | 2.2 | High | Auto-label ICs
2.3.2 | Detect ocular, muscle, and cardiac components | J | 18/12/25 | 19/12/25 | 2 | 2.3.1 | High | Visual verification of artifact ICs
2.4 | Artifact Removal | J | 22/12/25 | 31/12/25 | 7 |  |  | ICA + ASR (cleaning phase)
2.4.1 | Apply Independent Component Analysis (ICA) → remove artifactual Ics | J | 22/12/25 | 24/12/25 | 3 | 2.3.2 | High
2.4.2 | Use Artifact Subspace Reconstruction (ASR) for dynamic correction | J | 29/12/25 | 31/12/25 | 3 | 2.4.1 | High
2.5 | Filtering | A | 2026-02-01 | 2026-03-01 | 2 | 2.4.2 | High | Final band-limit filter
2.6 | Epoching | A | 2026-05-01 | 2026-07-01 | 3
2.6.1 | Resting state: 2 s non-overlapping windows | A | 2026-05-01 | 2026-05-01 | 1 | 2.5 | Medium | Resting-state segment prep
2.6.2 | Oddball: −200 ms to +800 ms around stimulus events | A | 2026-06-01 | 2026-06-01 | 1 | 2.5 | Medium | ERP epoching
2.6.3 | Apply baseline correction using pre-stimulus interval | A | 2026-07-01 | 2026-07-01 | 1 | 2.6.2 | Medium
2.7 | Feature Extraction/Transformation | D | 2026-08-01 | 20/01/26 | 9
2.7.1 | Time domain: Mean, variance, Hjorth parameters, entropy | D | 2026-08-01 | 2026-09-01 | 2 | 2.6.3 | Medium
2.7.2 | Frequency domain: PSD (Welch), theta/alpha/beta/gamma band power ratios | D | 2026-10-01 | 13/01/26 | 4 | 2.7.1 | High | Compute alpha/beta/theta powers
2.7.3 | Connectivity: coherence, phase-locking value (PLV) | D | 14/01/26 | 15/01/26 | 2 | 2.7.2 | Medium | Inter-channel metrics
2.7.4 | Time-frequency maps via Short-Time Fourier or wavelet transform | D | 16/01/26 | 17/01/26 | 2 | 2.7.3 | High
2.7.5 | Compute theta-to-alpha transition frequency (Transfreq) metrics for cognitive slowing | D | 19/01/26 | 20/01/26 | 2 | 2.7.4 | Medium | TF-aligned bands for cognitive metrics
Scrum 3 — Modeling
3.1 | Split data into train/val/test (70/15/15) | All | 21/01/26 | 22/01/26 | 2 | 2.7.5 | Low
3.2 | Model options | All | 23/01/26 | 2026-02-23 | 11
3.2.1 | EEGNet | D | 23/01/26 | 26/01/26 | 4 | 3.1 | High | Benchmark model — must be completed
3.2.2 | CNN/LSTM hybrid (for temporal–spatial features) | A | 27/01/26 | 30/01/26 | 4 | 3.2.1 | Medium
3.2.3 | 1D-CNN for raw EEG | J | 27/01/26 | 30/01/26 | 4 | 3.2.1 | Medium | Quick baseline alternative
3.2.4 | 2D-CNN for spectrograms | A | 31/01/26 | 2026-03-02 | 4 | 3.2.3 | Low
3.2.5 | Transformer-based sequence models | D | 2026-03-02 | 2026-02-06 | 4 | 3.2.4 | Low | Experimental, not required for MVP
3.3 | Implement regularisation (dropout, batch norm) | J | 2026-02-07 | 2026-02-11 | 5 | 3.2.1–3.2.3 | Medium
3.4 | Hyperparameter tuning (learning rate, optimiser, layers) | All | 2026-02-12 | 23/02/26 | 10 | 3.3 | High | Critical for achieving final model performance
Scrum 4 — Evaluation
4.1 | Compute all evaluation metrics on test set
4.2 | Cross-subject testing (leave-one-subject-out)
4.3 | Compare performance across EEG paradigms (Rest vs. Oddball)
4.4 | Generate confusion matrix, ROC curves, and reliability plots
4.5 | Evaluate model robustness under noise or reduced electrode subsets
Scrum 5 — Product Deployment