## Status Report
EEG-Based Parkinson’s Disease Diagnosis
Today's date: 2nd December 2025
Summary |  |  |  | Overall Status (RAG)
We are currently in Sprint 1 - Research Phase of the project. The team will be reviewing literature on Parkinson’s disease, EEG-based biomarkers, and challenges related to early diagnosis. We will be also exploring the 3-Stim Auditory Oddball & Rest EEG dataset to understand its structure, the types of artefacts present, and how suitable it is for building a model. At this stage, we are identifying key challenges such as noisy EEG signals, the difficulty of detecting early PD patterns, and ensuring the final model is interpretable for clinical use. Each team member will be focusing on their assigned research area: artefact detection and deployment, feature extraction and evaluation metrics, and filtering, epoching, and modelling. The work completed in this phase will guide our next steps, which include designing the preprocessing pipeline, choosing our initial modelling approaches, defining a clear evaluation strategy, and exploring possible deployment options for the final prototype. This report also highlights early risks and the actions we plan to take as we prepare to move into the implementation stage, where coding and experimentation will begin. |  |  |  | Amber
Completed Milestones and Tasks
Description | Date | Status | Owner |  | Comments
Project Initiation
Group Contract outlining expectations, communication, and teamwork guidelines | 10 October 2025 | Completed | Team
Project Charter, including goals, scope, deliverables, and ethical framework and Project Timeline | 21 October 2025 | Completed | Diba
Objectives & Key Results (OKRs) for technical and organisational progress | 21 October 2025 | Completed | Aleeza |  | OKRs will have versions as the project progresses to reflect new finding and technical decisions.
Risk Management Plan identifying early risks and mitigation strategies | 11 November 2025 | Completed | Aleeza
Initial Project Plan (Excel) outlining tasks, timelines, dependencies, and sprint structure | 11 November 2025 | Completed | Diba |  | The project plan will be updated as tasks become clearer, helping us understand dependencies, adjust the timeline, and plan each stage properly.
Communication Plan detailing communication types, recipients, frequency, delivery methods, and goals | 11 November 2025 | Completed | Justyna
Upcoming Milestones and Tasks
Description | Date | Status | Owner |  | Comments
Complete Individual Research Assignments for the January submission. | Dec - Jan | Upcoming | Team |  | Each member finalises their research area (artefacts, features, modelling).
Filtering Research: review low-pass, high-pass, and band-pass filters to understand how to clean EEG signals. | Dec - Jan | Upcoming | Aleeza |  | Essential for removing unwanted frequencies before further processing.
Segmentation/Epoching Research: explore how to segment signals into meaningful time windows for analysis. | Dec - Jan | Upcoming | Aleeza |  | Determines how signals will be divided for analysis and modelling.
Channel Selection: identify which EEG channels and brain regions (e.g., frontal/central, alpha/beta activity) are most relevant for Parkinson’s detection. | Dec - Jan | Upcoming | Team |  | Supports feature selection and understanding PD-related brain activity.
Artifact Detection & Cleaning: study methods for identifying and removing eye blinks, muscle noise, and cardiac artefacts to improve signal quality. | Dec - Jan | Upcoming | Justyna |  | Important for improving signal quality
Feature Extraction & Selection: investigate frequency bands (alpha, beta, theta), PSD features, and other signal characteristics to support classification. | Dec - Jan | Upcoming | Diba |  | Determines which features will be used in early modelling.
Review modelling and deployment approaches, and identify evaluation metrics that will be used to assess model effectiveness. | Dec - Jan | Upcoming | Team |  | Helps shortlist suitable models and choose evaluation metrics that match the project scope, and expected model performance.
Top Risks and Issues
Issue |  | Impact | Action |  |  | Owner
Team illness |  | May slow down individual research tasks or delay meetings | Allow flexible working, redistribute small tasks temporarily, keep detailed notes so others can follow progress. |  |  | Team
Workload from other assignments |  | Could reduce available time for this project and affect progress | Plan tasks weekly, update team frequently, and break tasks into smaller, manageable steps |  |  | Team
Bad weather affecting in-person meetings |  | May disrupt scheduled group meetings on campus | Switch to online meetings (Teams/Zoom) and increase use of group chat for quick updates |  |  | Scrum Master
Research tasks taking longer than expected |  | Could cause delays in the next stage (implementation) | Prioritise essential research first and adjust the timeline if needed. |  |  | Task Owner/Scrum Master