## Exemplar
ROAM Analysis
| Issues | Actions | ROAM designation
Issue 1 | Project momentum slowed slightly during the winter vacation period. While the research phase was completed by the end of the break, implementation did not begin as early as planned. | The team held catch-up group meetings after the vacation to consolidate individual research findings into a single, agreed pipeline. Research outputs were mapped directly to preprocessing and modelling steps to enable a smooth and timely transition into the implementation phase. | Mitigated
Issue 2 | Team members experiencing illness due to dropping temperatures, resulting in absence during Sprint 1. | The affected team member continued working remotely to complete assigned research tasks. The team coordinated to ensure all required work was completed in time for the progress presentation. | Resolved
Issue 3 | Difficulty finding a large number of research papers directly using the EEG: 3-Stim Auditory Oddball and Rest in Parkinson’s dataset. | The research scope was expanded to include closely related EEG Parkinson’s studies, allowing relevant preprocessing approaches and modelling strategies to be adapted for this dataset. | Accepted
Issue 4 | Dataset originates from a US-based population, which may affect generalisability and comparison with UK clinical studies. | This limitation was acknowledged by the team, with generalisability treated as a factor to consider during model evaluation rather than a blocker to implementation. | Accepted
Issue 5 | Transitioning from research to implementation required agreement on model selection and evaluation strategy. | EEGNet was selected as the baseline model due to its suitability for EEG datasets, with CNN/XGBoost models planned for later comparison in the implementation phase (if we've got enough time). | Resolved