# Sprint Retrospective: Sprint 1 (Research and Planning Phase)
Date: 20th January 2026

Owner: Diba

Collaborators: Justyna and Aleeza

Status: Completed

# Sprint Summary

Sprint 1 focused on the research and planning phase of the project, to establish a solid technical and methodological foundation before moving into implementation. During this sprint, the team reviewed EEG-based Parkinson’s Disease literature, explored the characteristics of the 3-Stim Auditory Oddball and Rest EEG dataset, and evaluated suitable preprocessing and modelling approaches. The outcomes of this research were brought together into a clear pipeline that will be used to guide the implementation phase.

| Project Status: | Active |
| --- | --- |
| Sprint Goals and Objectives: | - Build a strong research and planning foundation for the implementation phase. - Review Parkinson’s-related EEG biomarkers in resting-state and auditory oddball paradigms. - Analyse the structure and limitations of the selected EEG dataset. - Identify best-practice EEG preprocessing methods, including artefact handling, filtering, and epoching. - Explore suitable feature extraction approaches, evaluation metrics, and baseline models such as EEGNet. - Combine research findings into a clear preprocessing and modelling pipeline for Sprint 2. |
| Duration of Sprint: | December – January |
| Team: | Sprint Owner: Diba Project Owner & Tester: Justyna Resource Allocator & Quality Assurance: Aleeza Ethical Analysis: Diba |
| Link to Sprint Doc(s) | Sprint Plan |
| Methodology: | Agile |
| Project Resources: | - EEG dataset (3-Stim Auditory Oddball and Rest in Parkinson’s) - OKRs - Risk Management - Research papers and review articles - Project Charter and Sprint Plan - Collaboration tools (GitHub, Canva) |

# Lessons Learned

## Things that went well:

- Research was completed within the sprint despite external disruptions.

- The team developed a strong understanding of EEG preprocessing and Parkinson’s-related neural patterns.

- Clear agreement was reached on preprocessing steps and baseline model selection.

- Collaboration and knowledge-sharing across team members was effective.

## Things that need improvement:

- Implementation could have started earlier alongside late-stage research.

- Momentum slowed slightly around the winter vacation period.

## Where we got lucky:

- Existing EEG best-practice literature helped compensate for limited dataset-specific studies.

- Team members were able to work remotely when needed, preventing major delays.

# Action Items

What actions should we take as a result of our lessons learned?

| Action Item | Type [tool, process, team] | Owner | Links |
| --- | --- | --- | --- |
| Convert research findings into a clear preprocessing and modelling pipeline | Process | SM | N/A |
| Start Sprint 2: EEG preprocessing for modelling | Process | SM | N/A |
| Hold regular group meetings to catch up, coordinate tasks, and manage project progress | Team | SM | N/A |

# Future Considerations

What would we recommend future projects of a similar nature mitigate or design contingency plans for?

| Risk | Type [technical, process, team, schedule] | Contact | Link(s) |
| --- | --- | --- | --- |
| Dataset limitations impacting model performance and robustness | Technical | Project Owner/ Client | N/A |
| Overfitting due to limited dataset size, which may reduce model generalisation | Technical | Scrum Master | N/A |