## Sprint Plan
Sprint Plan
Sprint No | Sprint Goal | Sprint Tasks | Start Date | End Date | ScrumMaster | Daily Stand-up | Daily Stand-up | Daily Stand-up | Daily Stand-up | Daily Stand-up | Daily Stand-up | Daily Stand-up | Sprint Review
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Project Initiation | For the Scrum master to lead the team to ensure an effective start of the project making sure that all the tasks are completed on time and within the timeframe so that the team stays on track from the beginning. For the Scrum Team to underntand the project aims and objectives and the project goal in order to start off the project well. For the scrum Team to complete all the Sprint 1 tasks up to the highest standards agreed in the group contract To understand the project including the dataset provided. | Complete Group Project Team Roles Test to be completed by every member To decide on the Aims and Objectives To create the GitHub Repository To decide on the Project requiremenets To decide on the Development Methodology To create Mictrosoft Project schedule To create the Risk Mangement Table To understand the features of the dataset | 2025-10-07 | 2025-11-18 | Justyna | Date: 07/10/2025 | Date: 29.10.2025 | Date: 05.11.2025 | Date: 10.11.2025 | Date: 11.11.2025 | Date: 12.11.2025 | Date: | Date: 10.11.2024
[6 empty] | Meeting Time:12pm | Meeting Time:14:00 and 15:00 | Meeting Time: 11am and 2pm | Meeting Time: 10am | Meeting Time: 11am | Meeting Time: 11am | Meeting Time: | Meeting Time: 12pm
[6 empty] | Today we held a team meeting and created our group contract, agreeing on shared goals, expectations, working policies and consequences to support effective collaboration throughout the project. | Today we held a team meeting and created our group contract, agreeing on shared goals, expectations, working policies and consequences to support effective collaboration throughout the project. | Today we held a team meeting where we defined our project goals and scope, reviewed the ethical and legal framework, and agreed on success criteria for model performance and clinical relevance. We also created a project document outlining the budget overview, key deliverables, team strengths, and potential risks to guide the next stages of development. | Today we met with our client and stakeholder to discuss the EEG Parkinson’s dataset and overall research direction. We reviewed the dataset structure and agreed on key research tasks, including understanding Parkinson’s disease characteristics, exploring the dataset in detail, selecting the most relevant EEG channels, investigating artefact detection and cleaning methods, and planning feature extraction approaches to support later model development. | Today we held a team meeting to decide on our project management approach. We discussed the CDIO framework and compared it with Agile. We agreed to use CDIO as our main framework to guide the project from conception to deployment, while also applying Agile practices such as short sprints, regular meetings and continuous feedback to support flexible and iterative development. | Today we created our risk management document and risk assessment table. We identified key project risks across team management, technical and computational challenges, and data/model performance. For each risk, we defined potential impacts, probability, indicators, and mitigation strategies, such as backup task allocation, managing GPU limitations, applying artefact cleaning, and preventing model overfitting to ensure smooth project progression. |  | As a scurmmaster, Justyna led the team to ensure an effective start to the project, keeping tasks on track and supporting timely completion of planned activities. The Product Owner(Justyna) facilitated communication with the client and stakeholders, arranged stakeholder meetings, gathered project requirements, and created the initial product backlog to translate project needs into clear and prioritised tasks. As a team, we developed a clear understanding of the project aims, objectives, and overall project goal. We explored the Parkinson’s disease EEG dataset, discussed the project scope, and gained initial insight into the dataset structure and research direction. We also completed key initiation tasks to the standard agreed in the group contract, including setting up project documentation, defining goals and scope, creating the team contract, risk management plan, and agreeing on the project management approach using CDIO supported by Agile practices. All planned Sprint 1 tasks were completed successfully, and there were no outstanding items in the backlog at the end of the sprint. **Actions for Next Sprint:** In the next sprint, the team will begin detailed dataset exploration, research EEG channel selection, investigate artefact detection and cleaning methods, and plan feature extraction approaches to prepare for model development.
Sprint 1 | The goal of Sprint 1 is to build a strong research and planning foundation for the project. We aim to ensure the team understands the project aims, objectives, dataset, and overall project direction. Research topics will be assigned to each team member, and continuous communication with the stakeholder will be maintained to confirm expectations. A communication and project management plan will be created to support regular project updates. On the technical side, we will explore the Parkinson’s EEG dataset structure, participant groups, recording parameters, and data quality. We will conduct literature mapping on EEG-based Parkinson’s diagnosis, study artefact detection and removal methods, filtering best practices, feature extraction techniques, and relevant deep learning models. Findings will be summarised to define a default preprocessing and modelling pipeline, and the project environment will be set up for future development. | Agree on specific research topics and responsibilities for each team member. Conduct individual research on assigned topics and produce a short research report summarising key findings. Explore and understand the Parkinson’s EEG dataset, including structure, metadata, and data quality. Create a research map and research mind-map to visualise key investigation areas. Develop a design thinking mind-map to connect user needs, technical solutions, and project goals. Create project management documents, including a communication plan, project management plan, and project status reporting template. Produce risk management documentation, including a fishbone diagram and risk assessment table. Create the initial product backlog reflecting research and planning activities. Present key research findings and project planning documents to stakeholders for feedback and confirmation of direction. | 2025-11-18 | 2026-01-20 | Diba | Date: 18.11.2025 | Date: 22.11.2025 | Date: 24.11.2025 | Date: 10.12.2025 | Date: 20.01.2026 | Date: | Date: | Date: 05.02.2025
[6 empty] | Meeting Time: 10am | Meeting Time: 10:00 - 15:00 | Meeting Time: 11:00 - 14:00 | Meeting Time: 11:00 - 15:00 | Meeting Time: 10:00-17:00 | Meeting Time: | Meeting Time: | Meeting Time: 10:00-11:00
[6 empty] | Today we held a team meeting where we agreed on specific research responsibilities for each team member. Justyna will focus on artefact detection and cleaning methods, as well as researching deployment strategies for the final model. Diba will research feature extraction techniques and evaluation metrics to support effective model training and performance assessment. Aleeza will investigate filtering and epoching methods and explore suitable machine learning and deep learning models for the dataset. We also reviewed the first version of our Project Management Plan and agreed that it will be continuously refined and later transferred to a structured tracking tool such as Jira or Monday.com. | Today we held a team meeting where we created key project management documents to support structured project delivery. We developed the Project Management Plan to outline task timelines, responsibilities, and progress tracking, and created a Communication Plan to define how the team and stakeholders will stay informed throughout the project. We also reviewed these documents together to ensure alignment with project goals and agreed that they will be updated regularly as the project progresses. | Today we created our first Project Status Report to document current progress, completed tasks, and upcoming activities. We presented this report to the stakeholder to provide an update on project direction and early achievements. The Product Owner facilitated the meeting, ensured the stakeholder was satisfied with progress, and captured feedback, which was taken onboard to guide the next steps of the project. | Today we held a team meeting where we created key research and design diagrams to guide our project direction. We developed research mind-maps to structure our investigation areas across data preparation, modelling, deployment, and cross-team integration, and created a design-thinking mind-map to connect user needs, technical solutions, and expected outcomes. These diagrams align with our sprint goals by clarifying research focus, assigning responsibilities, and visualising the full project pipeline. They will help keep the team aligned, support structured research progression, and provide a clear roadmap for moving into the implementation phase. | Today we held a team meeting to share and discuss the research completed by each team member. We combined our findings on dataset understanding, artefact detection and cleaning, filtering and epoching, feature extraction, modelling approaches, and evaluation methods. Based on this discussion, we agreed on a unified preprocessing and modelling pipeline that will guide us through the next phase of technical implementation and model development. |  |  | As the Scrum Master for Sprint 1, Diba led the team and made sure everything stayed organised and on track. This sprint was mainly about building a strong foundation before moving into the technical work. We focused on understanding the Parkinson’s EEG dataset, including its structure, participant groups, and data quality. Each team member also researched key areas like artefact removal, filtering, epoching, feature extraction, and possible modelling approaches. This helped us get a clear idea of how the project will be carried out. On the project side, we created important documents such as the project management plan, communication plan, and risk assessment. We also developed research maps and diagrams to visualise the overall pipeline and keep everyone aligned. We shared our progress with the stakeholder and received early feedback, which confirmed we are moving in the right direction. As a team, we also agreed on a clear preprocessing and modelling approach for the next sprint. I would say Sprint 1 went quite well. With Diba leading as Scrum Master, the team stayed focused and organised. We now have a clear plan and are ready to move into Sprint 2 for preprocessing.
Sprint 2 | The goal of Sprint 2 is to focus entirely on EEG data preprocessing and move from planning into hands-on technical implementation. This sprint aims to apply core preprocessing steps, including filtering, artefact detection, epoching, and feature extraction, in a structured and validated manner. The focus is on building a clean, reliable, and extensible preprocessing pipeline that will directly support later modelling using EEGNet. Alongside technical implementation, project management activities will continue, including maintaining and updating project documentation, managing version control through GitHub, and maintaining a test plan to track preprocessing validation. Relevant diagrams and pipeline visualisations will also be developed to clearly document the preprocessing workflow. Ethical considerations will be actively reviewed during this sprint, including initial exploration and selection of an appropriate ethical toolkit to support responsible AI development and ensure compliance with ethical and regulatory requirements. | Implement EEG data preprocessing through structured and role-based coding tasks. Justyna to implement artefact detection and removal techniques, limiting artefact types to avoid overcomplication. Aleeza to implement epoching of EEG signals following filtering and artefact handling. Diba to implement feature extraction methods to prepare data for model training. Ensure preprocessing steps are modular and can be extended in later stages of the pipeline. Maintain and update project management documentation alongside technical work. Use GitHub for version control, code integration, and collaboration. Maintain and update a test plan to validate preprocessing steps. Create and refine preprocessing diagrams and pipeline visualisations. Review ethical considerations alongside development and begin identifying a suitable ethical toolkit for the project. Keep the group blog updated after each major preprocessing step to document progress, decisions, and reflections. Collect feedback from the client after major preprocessing stages and adjust decisions where required | 2026-01-20 | 2026-03-29 | Aleeza | Date: 20.01.2026 | Date: 21.01.2026 | Date: 16.02.2026 | Date: 17.02.2026 | Date: 24.02.2026 | Date: 24.02.2026 | Date: 28.02.2026 | Date: 29.02.2026
[6 empty] | Meeting Time: 14:00 - 15:00 | Meeting Time:16:00 -19:00 | Meeting Time: 14:00 -20:00 | Meeting Time: 9:00-13:00 | Meeting Time: 9:00 - 10:00 | Meeting Time: 10:00 - 15:00 | Meeting Time: 11:00 - 13:00 | Meeting Time: 12:00 -12:30
[6 empty] | Today we held our second client meeting with Ali, where he reviewed our Sprint 1 outcomes and the progress presentation in detail. He provided clear and constructive feedback on how we should approach Sprint 2 and emphasised the importance of focusing entirely on EEG preprocessing before moving into any modelling or experimentation. He specifically highlighted band-pass and notch filtering as essential first steps, followed by artefact detection, while advising us to limit the number of artefact types to three or four to keep the pipeline simple and manageable. He also confirmed that epoching and feature extraction should only be carried out once the data has been properly filtered and cleaned. During the discussion, we clarified expectations around preprocessing quality and validation, and agreed that regular client feedback would be beneficial. As a result, the team decided to seek feedback after each major preprocessing stage to ensure alignment with client expectations and to allow early corrections if needed. This meeting provided a clear technical direction for Sprint 2 and helped confirm priorities before starting implementation. | Today we held a three-hour team working session focused on starting the technical implementation for Sprint 2. The main objective of this session was to begin applying filtering to the EEG signals and to establish a clean and well-structured preprocessing pipeline. During this session, Aleeza focused on implementing EEG filtering, including notch and band-pass filtering, using a reduced and relevant set of EEG channels linked to motor and cognitive processing. The resting-state EEG data was loaded, unnecessary channels were removed, and only the selected EEG channels were retained. At the same time, Diba and Justyna focused on maintaining and updating project management documentation and managing GitHub for version control to ensure code changes were properly tracked and organised. Throughout the session, the team actively discussed implementation decisions and supported one another where needed. The filtered EEG data was saved in a structured format to support later stages such as artefact detection, epoching, and feature extraction. The next planned step is to move on to artefact detection and removal, led by Justyna, once the filtering results have been reviewed and double-checked by the team to ensure correctness and consistency before progressing. | In Todays meeting, we focused on continuing the preprocessing phase of the EEG dataset, specifically artefact removal, epoching, and feature extraction. The artefact removal and epoching processes were successfully implemented and the code ran as expected, allowing us to generate clean segmented data ready for modelling. However, feature extraction proved to be more time-intensive than anticipated, so we decided to run it separately to ensure efficiency and avoid delays in the overall pipeline. Alongside the technical work, we also made strong progress on exhibition planning which we'll also be continue working on in the Applied AI Professional Module, completing the floor plan, risk assessment draft, evaluation form, registration form, exhibition timings, and flyer design. In the next meeting, we plan to finalise the remaining exhibition documentation, including the project charter, updated risk assessment, project timeline, costing, roles and responsibilities, on-stand marketing strategy, and the final checklist (first aid, water, pens, etc.). The main blocker currently is the processing time required for feature extraction, which may require optimisation or extended runtime to complete successfully. | In today’s meeting before Tuesday’s class, we mainly worked on structuring our design presentation and clearly explaining the technical side of the project. We went over the dataset again and made sure we’re confident in explaining our preprocessing pipeline. For artefact removal, we’re using ICA to separate out noise components like eye blinks and unwanted signals. For filtering, we’re applying band-pass filtering using both high-pass and low-pass filters to keep only the important frequency range. For epoching, we agreed that for the resting phase we’ll segment the data into 1–4 second windows, and for stimulus-based events, we’ll use 20% before the stimulus and 80% after to properly capture the brain’s response. All of this preprocessing is being done using MNE. We also discussed the overall design ideas, the algorithms, models, and techniques we’ll be using later, such as EEGNet and other deep learning approaches/traditional methods (SVM), and how feature extraction fits into that pipeline. For testing and validation, we talked about evaluating the model properly using metrics like accuracy, sensitivity, and looking at the confusion matrix to understand false positives and false negatives. We also mentioned the possibility of testing on different splits or even different datasets to check generalisation. | Meeting with Ramzi We had a really useful feedback meeting where we reviewed our preprocessing and feature extraction work so far. He clarified the difference between signal smoothing and filtering, and discussed better ways to visualise and analyse amplitude, frequency, and peak characteristics in the EEG signals. He also talked about ideas like rolling window analysis, peak prominence, dimensionality reduction (PCA), and other feature extraction techniques to strengthen our approach. We plan to test some of the suggested techniques and see what actually works best for our dataset. The focus is on refining feature extraction, ensuring good class separation, and keeping the preprocessing pipeline clear and justifiable before moving further into modelling. Blockers: The main challenge right now is deciding which techniques genuinely improve performance without overcomplicating the model. We also need to be mindful of computational time when testing multiple approaches, as running different extraction methods can be quite time-consuming. On top of that, we’re facing a few minor issues while working in VS Code, as the interface can be a bit confusing at times, especially when managing environments and running different scripts. However, overall progress is steady and we’re gradually working through these challenges. | After the meeting with Ramzi, we had our own group session to continue working on the code, mainly focusing on feature extraction. We’ve been trying to properly apply the feedback both Ali and Ramzi gave us. One of Ali’s key points was to revisit the epoch length and make sure it aligns correctly with the sampling rate of the dataset, rather than just selecting a random time window. So we’ve been reviewing the dataset’s sampling frequency and adjusting the number of samples per epoch accordingly to make sure it’s technically justified. We’ve also started transferring more of our coding into VS Code so we can make better use of tools like Claude or GitHub Copilot for debugging and recommendations. It’s been helpful for catching small issues and improving structure, although we’re still getting used to the interface as it can feel a bit confusing at times. Alongside the technical work, we’re also finalising our exhibition documents, including the risk assessment, flyer, and evaluation form. We’ve shown our room plan to Kulvinder as well to get feedback and make sure everything is aligned before the exhibition. So overall, we’re balancing both the technical development and the project management side at the same time. | We had our final meeting for this sprint where we reviewed the preprocessing work as a team and presented our progress to Ali. During this session, we walked through the preprocessing pipeline, including how the data was cleaned, segmented, and prepared for modelling. One of the key decisions discussed in this meeting was focusing on the oddball task data. We explained that this approach provides more relevant and structured brain responses compared to resting state data, making it more suitable for distinguishing between a Parkinson’s patient and a healthy control. This decision was agreed upon as it supports our overall aim of building a more reliable classification model. The meeting also gave us the opportunity to get feedback and confirm that we are moving in the right direction before progressing further. This helped us feel more confident about the preprocessing stage and ensured that our approach is aligned with expectations. We concluded the meeting by confirming that preprocessing is now complete and that the project is ready to move into Sprint 3, which will focus on modelling and evaluation | Sprint 2 was focused on preprocessing the EEG data and building a reliable pipeline to prepare it for modelling. As a team, we were able to successfully clean, structure, and segment the data, making it ready for the next stage. A key outcome from this sprint was the decision to focus on the oddball task data, as it provides more relevant brain responses for distinguishing between Parkinson’s and control participants. We also confirmed our approach with Ali, which gave us confidence that we are on the right track. the sprint went well, and we have now completed preprocessing and are ready to move into Sprint 3
Sprint 3 | The goal of Sprint 3 is to focus on modelling and evaluation, transitioning from data preparation into building and testing machine learning models. This sprint aims to implement and evaluate the EEGNet model for Parkinson’s Disease classification using the preprocessed oddball EEG data. The focus is on training the model in a structured and controlled way, applying cross validation, and tuning key hyperparameters such as learning rate, dropout, and regularisation techniques to improve performance and reduce overfitting. Model performance will be assessed using appropriate evaluation metrics, including accuracy, AUC ROC, balanced accuracy, and both epoch level and subject level predictions. In addition to deep learning, this sprint will also explore traditional machine learning approaches such as SVM and KNN, based on feedback received. This will allow for comparison between different modelling techniques, particularly in the context of working with a relatively small dataset, and help identify the most reliable and generalisable approach. Alongside technical development, project management activities will continue, including updating the project plan, maintaining a structured test plan for model evaluation, and managing version control through GitHub. Outputs such as learning curves, confusion matrices, and performance summaries will be generated and used to support analysis and decision making. Initial work on explainability will also be introduced using methods such as LIME or SHAP, to help interpret model predictions and support transparency. This sprint will also include early planning for the final presentation, including ideas for visualising the modelling pipeline, results, and key findings in the project poster.B13:K15 | Implement EEG modelling and evaluation through structured and role-based tasks. Diba to focus on implementing and improving the EEGNet model, including architecture adjustments and regularisation techniques. Justyna to support model evaluation and validation processes across different experiments. Aleeza to support data handling, testing, and performance tracking during model training. Experiment with EEGNet architecture, including layers, filters, and dropout to improve performance. Tune hyperparameters such as learning rate, dropout, and weight decay to reduce overfitting. Apply cross validation to ensure fair and reliable model evaluation at subject level. Monitor training and validation performance to identify overfitting and model behaviour. Analyse model results using metrics such as accuracy, AUC ROC, and balanced accuracy. Explore traditional machine learning models for comparison based on feedback received in later stages. Ensure modelling pipeline is clear, structured, and extendable for further improvements. Maintain and update project management documentation alongside modelling work. Use GitHub for version control, code integration, and collaboration. Maintain and update a test plan to validate model performance and evaluation strategy. Create and refine diagrams and visualisations for modelling pipeline and results. Incorporate explainability techniques such as LIME or SHAP to interpret model predictions. Keep the group blog updated after key modelling stages to document progress, challenges, and decisions. Collect feedback from the client after reviewing modelling results and adjust approach where required. | 2026-03-30 | 2026-04-09 | Justyna | Date: 31.03.2026 | Date: 01.04.2026 | Date: 02.04.2026 | Date: 05.04.2026 | Date: 07.04.2026 | Date: 09.04.2026 | Date: | Date: 09.04.2026
[6 empty] | Meeting Time: 10:00 - 15:00 | Meeting Time: 11:00 - 13:00 | Meeting Time: 9:30 - 16:00 | Meeting Time: 9:00 - 16:00 | Meeting Time: 12:00 - 19:30 | Meeting Time: 9:00 - 16:00 | Meeting Time: | Meeting Time: 16:00 - 16:30
[6 empty] | We had a focused session working on implementing EEGNet using the oddball task dataset. This dataset was chosen because it provides more meaningful and structured brain responses, making it easier to differentiate between a Parkinson’s patient and a healthy individual. During this meeting, we experimented with different aspects of the model, including adjusting hyperparameters such as learning rate and dropout, as well as modifying the model architecture like layers and filters. The aim was to improve performance while trying to reduce overfitting. We also reviewed training and validation results to understand how the model was behaving and whether it was learning useful patterns. Blockers: The main issue identified was overfitting, where the model performs well on training data but does not generalise well to validation data. Tracking different experiments and configurations was also slightly time-consuming. | Feedback with Ali We had a short feedback session with Ali where we presented our modelling progress and discussed the overfitting issue. He advised that this is common with small datasets and suggested exploring traditional machine learning approaches alongside EEGNet. Based on this, we decided to take this feedback forward and begin comparing different modelling approaches while continuing to refine EEGNet. Blockers: The main challenge is deciding which approach is most suitable while managing time effectively when testing multiple models. | In this meeting, we focused on applying the feedback received and planning the next steps. We continued improving EEGNet while also starting to explore traditional models for comparison. The team divided the work so we could test different approaches in parallel. Diba continued working on improving EEGNet, Justyna focused on implementing the SVM model, and Aleeza worked on the KNN model. This helped us explore multiple directions at the same time and make better use of our time. We also discussed how to compare results fairly using the same dataset and evaluation metrics across all models. The aim was to ensure that any differences in performance are meaningful and not due to inconsistencies in the setup. The focus of this meeting was to make sure our final model choice is based on performance, reliability, and how well it generalises, rather than just training accuracy. Blockers: The main challenge is ensuring fair comparison between models and avoiding spending too much time testing unnecessary variations. Another challenge is achieving a model that performs better than EEGNet, or identifying a traditional model that can match or improve its performance. We also need to focus on improving the confusion matrix results, especially reducing the false negative rate, as this is very important in a project like this where missing a Parkinson’s case could have serious implications. | In this meeting, we presented our latest modelling results to Ali, including the performance of EEGNet and the traditional models we have been testing. We discussed the challenges we have been facing, particularly around overfitting and the limitations in improving specificity and overall generalisation. Ali reviewed the results and explained that the performance we are achieving is expected given the size and nature of the dataset. He mentioned that in a similar project he worked on with a company using the same dataset, they achieved very similar results. He also highlighted that the results align with findings from existing research on this dataset, where performance improvements tend to plateau due to limited data and signal variability. This was reassuring for us, as it confirmed that the issues we are seeing are not due to mistakes in our approach, but are instead linked to the dataset itself. Ali was happy with the results and agreed that they are realistic and acceptable for this type of project. We discussed moving forward by focusing on clearly presenting and justifying our results rather than trying to force unrealistic improvements. The emphasis now is on comparing models, explaining limitations, and demonstrating a strong understanding of the modelling process. Blockers: The main challenge remains the limitations of the dataset, which restrict how much the models can improve. There is also a need to balance further experimentation with time constraints, making sure we focus on refining and explaining our results rather than over-testing. | In this meeting, we discussed our current progress on model development, focusing on the performance of the three models we are working with: KNN, SVM, and EEGNet. We reviewed the latest results and tested the models on a small hold-out set of 6 subjects to better understand how well they generalise to unseen data. We compared how each model performed in terms of predictions and consistency, and discussed the challenges we are still facing, particularly with generalisation and achieving balanced results across classes. We also explored using the best-performing fold from cross-validation to see if it improves overall performance. The team acknowledged that, while the results are not perfect, they are expected given the limitations of the dataset, including limited size and variability. The focus of the discussion was on improving the models where possible, but also recognising that there is a realistic limit to performance. We agreed that the next step is to continue refining the models over the next few days and work towards selecting the final model for deployment. The goal is to choose a model that is stable and reliable rather than trying to achieve unrealistic accuracy. We also discussed preparing to transition into the deployment phase using Streamlit, once the final model has been selected. Blockers: The main challenge remains the limitations of the dataset, which affect model performance and generalisation. There is also some uncertainty in selecting the best model. Time constraints are becoming a factor, so we need to balance further improvements with moving forward to deployment. | In this meeting, we reviewed and compared the performance of all three models, KNN, SVM, and EEGNet, based on the updated testing using a 10-subject hold-out set. From this comparison, we decided to select SVM as our final model, as it achieved the best performance with an accuracy of around 90%. KNN produced the weakest results overall, while EEGNet achieved approximately 70% accuracy on the same data. We also observed that the SVM model did not miss any Parkinson’s cases during testing, which suggests that it has strong potential to generalise well, especially in identifying positive cases. This was an important factor in our decision, as sensitivity is critical for this type of diagnostic support system. We discussed some limitations we are currently facing with testing. Due to dataset constraints, we were unable to find suitable external datasets with target events to further validate the model. As a result, we are considering either testing further using our own dataset or reaching out to our client, Ali, to see if he can recommend or provide access to a more suitable dataset for additional validation. Alongside this, we have also started testing LIME and SHAP to see which method works better for our project in terms of explainability. The aim is to use these techniques during our presentation to clearly show how the model is making decisions. This will help us highlight which features are contributing most to the predictions and how important each feature is, making the model more transparent and easier to understand for our audience. In addition, we are working on developing a structured test plan for the final versions of all models (KNN, SVM, and EEGNet). We are also updating the sprint plan and continuing work on key project diagrams, including the modelling pipeline, preprocessing workflow, and user case diagrams. We have now started transitioning into the deployment phase, with a focus on implementing the selected SVM model using Streamlit. At the same time, we have begun working on the project poster in preparation for the final exhibition. |  | During this sprint, we moved from preprocessing into building and evaluating our models for Parkinson’s Disease classification using EEG data. We implemented EEGNet using the oddball dataset and tuned key parameters to improve performance, although overfitting remained a challenge due to dataset limitations. Based on feedback, we also developed and tested traditional models (SVM and KNN) to allow for comparison. Using cross-validation and hold-out testing (6 and 10 subjects), we found that SVM performed the best, achieving around 90% accuracy. EEGNet achieved around 70%, while KNN had the weakest results. Importantly, SVM did not miss any Parkinson’s cases, making it the most reliable option for our project. We also began exploring LIME and SHAP to improve model explainability. This will help us show how the model makes decisions by highlighting which features contribute most to predictions. Alongside modelling, we updated the sprint plan, worked on diagrams such as the modelling and preprocessing pipelines, and started developing a structured test plan for all models. Overall, this sprint allowed us to confidently select SVM as our final model. We will now move into deployment using Streamlit and focus on preparing our final presentation and poster.
Sprint 4 | The goal of Sprint 4 is to deploy our final Parkinson’s classification model (SVM) as a working and user-friendly application using Streamlit, while also preparing for the final project exhibition. This sprint focuses on building an interactive Streamlit interface where users can input EEG data and receive a clear classification between Parkinson’s Disease and a healthy control. The aim is to ensure the app is simple, reliable, and clearly shows how the model works, including outputs like prediction confidence where possible. We will also test the application to make sure it runs smoothly and produces consistent results. Alongside deployment, we will work on the final project poster, including key sections such as the problem, methodology, preprocessing, modelling, results, model comparison, final model justification, limitations, and future work. The poster will also include our ethical toolkit results to show how ethical considerations have been addressed. We will also record a demonstration video of the Streamlit app to support our presentation and clearly show how the system works. Finally, we will complete exhibition preparations, including printing materials and setting up for the showcase, while continuing to update documentation, version control, and final testing. The system will be clearly presented as a demonstration tool and not for clinical use. | Implement the Streamlit application to load the trained model and allow user interaction. Integrate the final trained model into the application for real-time classification. Design a simple and clear user interface to input EEG data and display classification results. Display outputs such as prediction (PD or Control) and confidence score. Ensure consistency between training and deployment pipelines. Test the application using sample EEG data to validate performance and stability. Handle errors and edge cases such as missing or incorrect inputs. Include an explainability component such as LIME or SHAP to provide insight into model decisions. Apply an ethical toolkit to review fairness, transparency, and responsible use of the model. Clearly communicate ethical limitations within the application. Work on the final poster design, ensuring it clearly explains the project, methodology, and results. Prepare and print any artefacts or materials required for the exhibition board. Plan and organise exhibition setup, including layout and presentation structure. Review and finalise catering arrangements for the exhibition. Ensure all exhibition requirements are completed and ready before the event. Maintain and update project documentation alongside development. Use GitHub for version control, integration, and collaboration. Update the test plan to include deployment and application testing. Create interface designs and system flow diagrams for the final presentation. Keep the group blog updated with deployment progress and reflections. | 2026-04-09 | 2026-04-16 |  | Date: 13.04.2026 | Date: 14.04.2026 | Date: 15.04.2026 | Date: | Date: | Date: | Date: | Date: 15.04.2026
[6 empty] | Meeting Time: 9:00 - 16:00 | Meeting Time: 10:30 - 15:00 | Meeting Time:10:00 - 15:00 | Meeting Time: | Meeting Time: | Meeting Time: | Meeting Time: | Meeting Time: 15:00 - 15:30
[5 empty] | Diba | In this meeting, we began working on the deployment phase of the project, focusing on building the Streamlit application for our final SVM model. The aim is to create a clean and user-friendly interface that clearly demonstrates how the model works. We started developing key sections of the app, including an “About Us” page to introduce the project and team, and a section to display the results from our ethical toolkit to highlight responsible AI considerations. We also worked on integrating the model outputs into the app, including displaying the prediction along with a confidence score to make the results more understandable for users. In addition, we began integrating the preprocessing pipeline into the application so that any input EEG data is automatically preprocessed before being passed into the model. This ensures consistency between training and real-time predictions. Alongside the app development, we also started working on the project poster, focusing on structuring the content and deciding what key information and visuals to include. | In this meeting, we finalised the project poster and confirmed all the content that will be included. We structured the poster using the CDIO approach, so it clearly shows the full process from concept to implementation and deployment, making the flow of the project easier to understand for the audience. We also completed recording the demo video of the Streamlit application, which will be used during the presentation to show how the system works in practice. In addition, the MS Project plan has now been completed, giving a clear overview of the project timeline and progress. On GitHub, we have updated and finalised the repository, including a detailed README file. This includes all supporting evidence of our group work, such as the ethical assessment and implications, quality and references, and a FAIR report summary. The ethical considerations and results from our ethical toolkit will also be included on the poster to clearly show how responsible AI has been addressed within the project. | In this meeting, we focused on reviewing all final materials to ensure everything is complete and correctly formatted before moving into the Scrum closure phase. We carefully checked the poster using the template provided by Kulvinder to make sure all sections are clear, visually balanced, and aligned with the project requirements. We reviewed the content to ensure consistency across the poster, demo, and supporting documents, including correct terminology, accurate results, and clear explanations. Any final adjustments were made to improve clarity, layout, and overall quality of the poster. We also confirmed that all required elements are included, such as the CDIO structure, ethical toolkit results, model outputs, and supporting visuals. This step was important to ensure that the poster is ready for the exhibition and clearly communicates our project to the audience. | Discussion of: Yesterday achievements, today’s plans and blockers: | Discussion of: Yesterday achievements, today’s plans and blockers: |  |  | During this sprint, we successfully transitioned from model development into deployment by building a functional and user-friendly Streamlit application for our final SVM model. The application was designed to clearly demonstrate how the model works, allowing users to input EEG data and receive a classification output along with a confidence score. We developed key features within the app, including an “About Us” section and a dedicated area to present the results from our ethical toolkit, ensuring responsible AI considerations are clearly communicated. We also integrated the preprocessing pipeline into the application so that all input data is processed consistently before prediction, maintaining alignment between training and deployment. Alongside the application development, we completed the project poster and structured it using the CDIO approach, making the overall workflow of the project clear and easy to follow for the audience. The poster includes all key elements such as methodology, modelling, results, model justification, and ethical considerations. We also recorded a demonstration video of the Streamlit application to support our explanation during the exhibition. In addition, the MS Project plan was finalised, and the GitHub repository was fully updated with a detailed README file and supporting evidence, including ethical assessment, quality and references, and a FAIR report summary. Final adjustments were made to improve clarity and layout, ensuring the poster and supporting materials are ready for the exhibition.
Scrum Closure | The goal of the Scrum Closure phase is to ensure all project deliverables are complete, well-organised, and ready for submission and exhibition, followed by reflecting on the project and formally closing it after the exhibition. | Review all GitHub folders to ensure complete evidence of work is included Organise and finalise all documentation (code, reports, ethical toolkit, test plans) Review and refine the project poster for clarity, layout, and visual appeal Ensure colour scheme and design are suitable for the exhibition audience Review and finalise the demo video, ensuring smooth playback and appropriate timing Practise timing alongside the demo to ensure clear explanation during the exhibition Confirm all materials are ready for submission and presentation Deliver the final exhibition and present the project Complete and submit the project closure report Complete the group evaluation form Upload final reflections and updates on the group blog | 2026-04-16 | 2026-04-22 | Aleeza | Date: 17.04.2026 | Date: 22.04.2026 | Date: | Date: | Date: | Date: | Date: | Date: 22.04.2026
[6 empty] | Meeting Time: 7:00 - 7:30 | Meeting Time: TBC | Meeting Time: | Meeting Time: | Meeting Time: | Meeting Time: | Meeting Time: | Meeting Time: TBC
[6 empty] | Daily Stand-Up Update (Before Exhibition) In this meeting, we focused on reviewing all project components to ensure everything is complete and ready for submission and the exhibition. We checked all GitHub folders to confirm that they include full evidence of our work, including code, documentation, ethical toolkit outputs, and test plans. We also reviewed the final poster to ensure it is visually clear and engaging for the audience, including checking the layout, structure, and colour scheme. The demo video was also reviewed to ensure it runs smoothly and has appropriate timing so that we can speak alongside it during the exhibition. The main focus of this meeting was to ensure everything is organised, finalised, and ready for submission and presentation. | Daily Stand-Up Update (After Exhibition): TBC | Discussion of: Yesterday achievements, today’s plans and blockers: | Discussion of: Yesterday achievements, today’s plans and blockers: | Discussion of: Yesterday achievements, today’s plans and blockers: |  |  | During the Scrum Closure phase, we focused on ensuring that all project deliverables were complete, well-organised, and ready for both submission and the final exhibition. This stage was important to bring together all parts of the project and confirm that everything meets the required academic and presentation standards. Before the submission, we reviewed all GitHub folders to make sure they included full evidence of our work, including code, documentation, ethical toolkit outputs, and test plans. We also finalised all documentation and ensured everything was clearly structured and easy to follow. The project poster was carefully reviewed and refined to improve clarity, layout, and visual appeal. We made sure the colour scheme and design were suitable for the exhibition audience and that all key information was presented clearly. The demo video was also finalised and tested to ensure smooth playback and appropriate timing, allowing us to confidently present alongside it. We confirmed that all materials were ready for submission and successfully delivered the final exhibition, where we presented our project and demonstrated the Streamlit application. After the exhibition , the focus will shift to formally closing the project. This will include completing and submitting the project closure report and the group evaluation form. We will also upload final reflections on the group blog, summarising the overall project, including what went well, the challenges faced, and what we have learned throughout the process. This stage will ensure that all final deliverables are submitted and that the project is fully completed and closed.